## Bug Reports
DEFECT ID | MODULE NAME | RELEASE VERSION | SUMMARY | DESCRIPTION | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | SEVERITY | DEFECT PRIORITY | STATUS
1 | GUI | v1.1 | The GUI loads images twice by clicking the "MORE" button. | The GUI loads images twice by clicking the "MORE" button and sends the request twice. | 1. Go to https://thecatapi.com/ 2. Click to images/search 3. Click to "MORE" button 4. Check the request in Devtools | The GUI loads images once by clicking the "MORE" button. The GUI sends the request once by clicking the "MORE" button. | The GUI loads images twice by clicking the "MORE" button. The GUI sends the request twice by clicking the "MORE" button. | Minor | Low |  | Open | Blocker | High | Open
2 | GUI | v1.1 | The GUI doesn't load images when breed and category are requested at the same time. |  | 1. Go to https://thecatapi.com/ 2. Click to images/search 3. Set the Breed parameter as Abyssinian and Category as boxes. | The GUI loads images according to the requested parameters. | The GUI doesn't load images. | Major | Medium |  | Open | Major | Medium | Resolved
2 | Task description |  | Impossible load 18 and 80 images in a 3x3 grid. | The task contains the following description: "we should place API response with data grid placing images in 3x3 data table". |  | The task includes a grid description for values 9, 18, and 80 ("per page" parameter). | The task includes a grid description for a value of 9 only ("per page" parameter). | Major | High |  | Open | Minor | Low | Closed
3 | Task description |  | The "MORE" button description from the task description is different from the mockup. | The task description contains a button description as the blue "MORE" button, but the mockup displays the green "MORE" button. |  | The task description contains the same "MORE" button description as the mockup. | The task description contains a button description as the blue "MORE" button, but the mockup displays the green "MORE" button. | Minor | Low |  | Open | Low
4 | Task description |  | The task description contains a typo in the order parameter description. | The task contains the following description: "Order - options: Random Asc (order param = empty), Desc Asc (order param = desc), Asc (order param = asc)". |  | The task contains the following description: "Order - options: Random (order param = empty), Desc (order param = desc), Asc (order param = asc)". | The task contains the following description: "Order - options: Random Asc (order param = empty), Desc Asc (order param = desc), Asc (order param = asc)". | Low | Low |  | Open
5 | GUI | v1.1 | The GUI provides the random order parameter as "order=Random". |  |  | The GUI provides the empty value for the random order parameter. "order=" | The GUI provides the random order parameter as "order=Random" | Minor | Low |  | Open
7 | API | v1.1 | The API doesn't provide records when breed and category are requested at the same time. | The API provides the empty array. | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?breed_ids=abys&category_ids=5&limit=2&page=1 | The API provides records according to requested breed and category. | The API doesn't provide records when breed and category are requested at the same time. | Major | Medium |  | Open
8 | API | v1.1 | The API provides records not according to the requested descending order parameter. | order=Desc | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?breed_ids=beng&order=Desc&limit=3&page=0 | The API provides records according to the requested descending order parameter. | The API provides records not according to the requested descending order parameter. | Major | Medium |  | Open
9 | API | v1.1 | The API provides records not according to the requested ascending order parameter. | order=Asc | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?breed_ids=beng&order=Asc&limit=4&page=0 | The API provides records according to the requested ascending order parameter. | The API provides records not according to the requested ascending order parameter. | Major | Medium |  | Open
10 | API | v1.1 | The API provides records not according to default sorting. | Default sorting is ascending. The API response records have no ascending order. | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?breed_ids=beng&limit=4&page=0 | The API provides records according to default sorting | The API provides records not according to default sorting. | Major | Medium |  | Open
11 | API | v1.1 | The API provides records not according to the requested random order parameter. |  | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?breed_ids=beng&order=Rand&limit=4&page=2 | The API provides records according to the requested random order parameter. | The API provides records not according to the requested random order parameter. | Major | Medium |  | Open
12 | API | v1.1 | The API provides a 200 status code when the Breed list doesn't include breed_ids value. |  | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?limit=3&page=0&breed_ids=sddd | The API provides a 404 status code when the Breed list doesn't include breed_ids value. | The API provides a 200 status code when the Breed list doesn't include breed_ids value. | Major | High |  | Open
13 | API | v1.1 | The API provides a 200 status code when breed_ids is empty |  | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?limit=3&page=0&breed_ids= | The API provides a 404 status code when breed_ids is empty | The API provides a 200 status code when breed_ids is empty | Major | High |  | Open
14 | API | v1.1 | The API provides a 200 status code when the category list doesn't include category_ids value. |  | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?limit=3&page=0&category_ids=4f | The API provides a 404 status code when the category list doesn't include category_ids value. | The API provides a 200 status code when the category list doesn't include category_ids value. | Major | High |  | Open
15 | API | v1.1 | The API provides a 200 status code when category_ids is empty |  | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?limit=3&page=0&category_ids= | The API provides a 404 status code when category_ids is empty | The API provides a 200 status code when category_ids is empty | Major | High |  | Open
16 | API | v1.1 | The API provides 200 status code when the mime_types value is not supported |  | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?limit=3&page=0&mime_types=sdf | The API provides a 404 status code when the mime_types value is not supported | The API provides a 200 status code when the mime_types value is not supported | Major | High |  | Open
17 | API | v1.1 | The API provides a 200 status code when the request includes an invalid token |  | Should use postman app. 1. Set x-api-key header to request. token: 23175861-2e83-4516-9844-b5df09b11c49 2. Send request: https://api.thecatapi.com/v1/images/search?breed_ids=beng | The API provides a 401 status code when the request includes an invalid token | The API provides a 200 status code when the request includes an invalid token | Major | High |  | Open
18 | API | v1.1 | The API provides a 200 status code for unauthorized request. |  | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?category_ids=1 | The API provides a 401 status code for unauthorized request. | The API provides a 200 status code for unauthorized request. | Major | High |  | Open
19 | Task description |  | The one option of dropdown list from the task description is different from the mockup. | The task contains the following description: "we should place the dropdown with 3 options: 9, 18, 80". But the mockup displays the dropdown list with 3 options: 9, 18, and 27. |  | The task description contains the dropdown list description with 3 options: 9, 18 and 80. The mockup displays the dropdown list with 3 options: 9, 18 and 80. | The task description contains the dropdown list description with 3 options: 9, 18 and 80. The mockup displays the dropdown list with 3 options: 9, 18 and 27. | Minor | Low |  | Open | Minor | Low | Closed
20 | API | v1.1 | The API provides a 200 status code for the request that contains order=Rand, limit, and page. |  | 1. Should use postman app to send request: https://api.thecatapi.com/v1/images/search?breed_ids=beng&limit=3&page=0&order=Rand | The API provides a 200 status code for the request that contains order=Rand, limit, and page. | The API provides a 404 status code for the request that contains order=Rand, limit, and page. | Major | Medium |  | Open